## Guide
Employer Brand Campaign Tracker
Plan, run and report on recruitment marketing campaigns in one Excel file
What this workbook does
One place to plan campaign content, log results by channel, check the careers website, and keep track of tasks with recruiters, agencies and suppliers. Every number on the Dashboard and in the charts is a formula, so it changes the moment you change an entry.
Sheets
Dashboard | Headline numbers, results by channel and campaign, content and task status, careers page checks, and two charts.
Settings | The report date, the two targets, and the channel names.
Campaigns | One row per campaign: ID, name, goal, dates and status. Room for 20 campaigns; the Dashboard shows the first 8.
Content_Calendar | What is going out, when, on which channel, who owns it, and its status. Late items are flagged. Room for 300 rows.
Performance | Results by campaign and channel: impressions, clicks, careers page visits and applications. Room for 300 rows.
Careers_QA | A checklist for careers website pages: pass, needs update, or fail.
Tasks | Follow-ups with recruiters, agencies, suppliers and internal teams, with due dates. Late tasks are flagged.
How to use it
1 | Type only in the yellow cells with blue text. Other cells are formulas.
2 | Add each campaign on the Campaigns sheet, then use its Campaign ID on the other sheets.
3 | Set the report date, targets and channel names on Settings. Update the report date each time you refresh the report.
4 | Read the Dashboard.
Measures
CTR | Clicks divided by Impressions.
Visit-to-apply rate | Applications divided by Careers page visits.
Result | On target if CTR and visit-to-apply rate are both at or above the targets, otherwise Below target.
Overdue | A content item or task is Overdue when its date is before the report date and it is not Live, Done or (for tasks) Done.
Checks
Data check | Performance rows say Check numbers if Clicks are more than Impressions, Applications are more than Careers page visits, or any number is negative.
ID check | Flags a Campaign ID that is repeated on Campaigns, or used on another sheet but not listed on Campaigns.
Other rows | Anything on a channel or campaign that is not listed on Settings or Campaigns lands in the Other row, so Dashboard totals always match the data sheets.
IMPORTANT
Every row in this file is SAMPLE DATA for a fictional company. Delete the sample rows and enter your own before drawing any conclusion. The targets on Settings are assumptions, not industry figures.
Colour legend
Blue text, yellow cell | Type here (inputs).
Black text | Formula. Do not type here.

## Dashboard
Dashboard
Every number here is a formula built from the other sheets. Change an entry and this page and its charts update.
Data check: all rows OK
Headline numbers
Impressions / sends | Clicks | CTR | Careers page visits | Applications | Visit-to-apply rate
258582 | 7277 | 2.814% | 5933 | 258 | 4.349%
Results by channel
Channel | Impressions / sends | Clicks | CTR | Careers page visits | Applications | Visit-to-apply rate
LinkedIn | 78300 | 1627 | 2.078% | 1440 | 71 | 4.931%
Instagram | 48727 | 631 | 1.295% | 512 | 19 | 3.711%
Email | 72796 | 3478 | 4.778% | 2713 | 103 | 3.797%
Careers Website | 58759 | 1541 | 2.623% | 1268 | 65 | 5.126%
Other (not on Settings list) | 0 | 0 | 0% | 0 | 0 | 0%
Total | 258582 | 7277 | 2.814% | 5933 | 258 | 4.349%
Results by campaign
Campaign ID | Campaign | Content items | Live or done | Impressions / sends | Clicks | CTR | Applications | Visit-to-apply rate
C01 | Graduate Hiring Drive | 7 | 7 | 62827 | 1587 | 2.526% | 65 | 5.306%
C02 | Employee Stories Series | 7 | 6 | 56112 | 1679 | 2.992% | 65 | 4.758%
C03 | Campus Careers Week | 6 | 5 | 61477 | 1921 | 3.125% | 60 | 4.011%
C04 | Careers Site Refresh | 6 | 5 | 78166 | 2090 | 2.674% | 68 | 3.684%
Other | Not in the first 8 campaigns | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Total |  | 26 | 23 | 258582 | 7277 | 2.814% | 258 | 4.349%
Work status
Item | Count
Content: planned | 0
Content: in review | 3
Content: live | 5
Content: done | 18
Content: no status or other | 0
Content: overdue | 3
Careers page checks: pass | 11
Careers page checks: needs update | 3
Careers page checks: fail | 1
Careers page checks: pass rate | 73.33%
Tasks: open | 8
Tasks: overdue | 4

## Settings
Settings
Change the yellow cells. Everything else updates.
Setting | Value | Note | Channel names
Report date | 2026-10-25 | Used to flag overdue content and tasks. Update each time you refresh the report. | LinkedIn
Target CTR (clicks / impressions) | 2% | Author's assumption. Set your own goal. | Instagram
Target visit-to-apply rate | 4% | Author's assumption. Set your own goal. | Email
Careers Website
These names fill the Channel dropdowns and the Dashboard channel table.

## Campaigns
Campaigns
One row per campaign. The Campaign ID is used on every other sheet.
SAMPLE DATA: made-up entries for a fictional company, to show how the tracker works. Replace with your own.
Campaign ID | Campaign name | Goal | Start | End | Status | ID check
C01 | Graduate Hiring Drive | Get more graduates to start an application | 2026-09-01 | 2026-10-31 | Live | OK
C02 | Employee Stories Series | Show real employee experiences on social and email | 2026-09-08 | 2026-11-15 | Live | OK
C03 | Campus Careers Week | Promote campus events and the careers site | 2026-10-05 | 2026-10-16 | Done | OK
C04 | Careers Site Refresh | Update careers pages and measure candidate visits | 2026-09-15 | 2026-11-30 | Live | OK

## Content_Calendar
Content Calendar
One row per piece of content. Overdue is worked out from the report date on Settings.
SAMPLE DATA: made-up entries for a fictional company, to show how the tracker works. Replace with your own.
Publish date | Campaign ID | Channel | Content type | Topic | Owner | Status | Overdue? | ID check
2026-09-04 | C01 | Instagram | Web page update | Life as a graduate | Priya | Done |  | OK
2026-09-06 | C02 | Instagram | Employee story | Day in the life | Rahul | Done |  | OK
2026-09-07 | C03 | Email | Video | Meet the team | Neha | Done |  | OK
2026-09-10 | C04 | LinkedIn | Web page update | How to apply | Aman | Done |  | OK
2026-09-11 | C01 | LinkedIn | Post | Interview tips | Priya | Done |  | OK
2026-09-14 | C02 | Instagram | Email | Campus event recap | Rahul | Done |  | OK
2026-09-15 | C03 | Careers Website | Post | Career paths | Neha | In review | Overdue | OK
2026-09-17 | C04 | Careers Website | Web page update | Benefits overview | Aman | Done |  | OK
2026-09-20 | C01 | LinkedIn | Employee story | FAQ update | Priya | Done |  | OK
2026-09-21 | C02 | Email | Web page update | Team spotlight | Rahul | Done |  | OK
2026-09-23 | C03 | Email | Web page update | Life as a graduate | Neha | Done |  | OK
2026-09-25 | C04 | Careers Website | Post | Day in the life | Aman | In review | Overdue | OK
2026-09-27 | C01 | Instagram | Video | Meet the team | Priya | Done |  | OK
2026-09-29 | C02 | Instagram | Web page update | How to apply | Rahul | Done |  | OK
2026-10-01 | C03 | Email | Employee story | Interview tips | Neha | Done |  | OK
2026-10-04 | C04 | LinkedIn | Employee story | Campus event recap | Aman | Done |  | OK
2026-10-05 | C01 | LinkedIn | Web page update | Career paths | Priya | Done |  | OK
2026-10-07 | C02 | Instagram | Email | Benefits overview | Rahul | Done |  | OK
2026-10-10 | C03 | Careers Website | Post | FAQ update | Neha | Done |  | OK
2026-10-11 | C04 | Careers Website | Employee story | Team spotlight | Aman | Done |  | OK
2026-10-14 | C01 | LinkedIn | Employee story | Life as a graduate | Priya | Live |  | OK
2026-10-15 | C02 | Email | Email | Day in the life | Rahul | Live |  | OK
2026-10-18 | C03 | Email | Video | Meet the team | Neha | Live |  | OK
2026-10-20 | C04 | Careers Website | Post | How to apply | Aman | Live |  | OK
2026-10-21 | C01 | Instagram | Web page update | Interview tips | Priya | Live |  | OK
2026-10-23 | C02 | Instagram | Post | Campus event recap | Rahul | In review | Overdue | OK

## Performance
Performance
One row per campaign, channel and week. CTR, visit-to-apply rate and Result are formulas.
SAMPLE DATA: made-up entries for a fictional company, to show how the tracker works. Replace with your own.
Week starting | Campaign ID | Channel | Impressions / sends | Clicks | Careers page visits | Applications | Campaign name | CTR | Visit-to-apply rate | Result | Data check
2026-09-07 | C01 | LinkedIn | 7266 | 145 | 135 | 10 | Graduate Hiring Drive | 1.996% | 7.407% | Below target | OK
2026-09-07 | C02 | Instagram | 2508 | 27 | 25 | 0 | Employee Stories Series | 1.077% | 0% | Below target | OK
2026-09-07 | C03 | Email | 8651 | 538 | 413 | 8 | Campus Careers Week | 6.219% | 1.937% | Below target | OK
2026-09-07 | C04 | Careers Website | 12812 | 291 | 248 | 9 | Careers Site Refresh | 2.271% | 3.629% | Below target | OK
2026-09-14 | C01 | Instagram | 7598 | 92 | 86 | 5 | Graduate Hiring Drive | 1.211% | 5.814% | Below target | OK
2026-09-14 | C02 | Email | 4433 | 141 | 121 | 1 | Employee Stories Series | 3.181% | 0.8264% | Below target | OK
2026-09-14 | C03 | Careers Website | 10117 | 375 | 263 | 14 | Campus Careers Week | 3.707% | 5.323% | On target | OK
2026-09-14 | C04 | LinkedIn | 9830 | 217 | 205 | 14 | Careers Site Refresh | 2.208% | 6.829% | On target | OK
2026-09-21 | C01 | Email | 9368 | 470 | 321 | 14 | Graduate Hiring Drive | 5.017% | 4.361% | On target | OK
2026-09-21 | C02 | Careers Website | 5987 | 107 | 97 | 8 | Employee Stories Series | 1.787% | 8.247% | Below target | OK
2026-09-21 | C03 | LinkedIn | 12211 | 226 | 206 | 6 | Campus Careers Week | 1.851% | 2.913% | Below target | OK
2026-09-21 | C04 | Instagram | 8959 | 175 | 145 | 8 | Careers Site Refresh | 1.953% | 5.517% | Below target | OK
2026-09-28 | C01 | Careers Website | 3189 | 133 | 94 | 3 | Graduate Hiring Drive | 4.171% | 3.191% | Below target | OK
2026-09-28 | C02 | LinkedIn | 15159 | 362 | 325 | 13 | Employee Stories Series | 2.388% | 4% | On target | OK
2026-09-28 | C03 | Instagram | 3717 | 34 | 28 | 0 | Campus Careers Week | 0.9147% | 0% | Below target | OK
2026-09-28 | C04 | Email | 12351 | 497 | 415 | 9 | Careers Site Refresh | 4.024% | 2.169% | Below target | OK
2026-10-05 | C01 | LinkedIn | 12121 | 263 | 216 | 16 | Graduate Hiring Drive | 2.17% | 7.407% | On target | OK
2026-10-05 | C02 | Instagram | 5495 | 84 | 62 | 1 | Employee Stories Series | 1.529% | 1.613% | Below target | OK
2026-10-05 | C03 | Email | 12501 | 449 | 317 | 21 | Campus Careers Week | 3.592% | 6.625% | On target | OK
2026-10-05 | C04 | Careers Website | 11575 | 262 | 244 | 18 | Careers Site Refresh | 2.263% | 7.377% | On target | OK
2026-10-12 | C01 | Instagram | 12388 | 114 | 75 | 1 | Graduate Hiring Drive | 0.9202% | 1.333% | Below target | OK
2026-10-12 | C02 | Email | 10894 | 671 | 484 | 31 | Employee Stories Series | 6.159% | 6.405% | On target | OK
2026-10-12 | C03 | Careers Website | 6710 | 188 | 173 | 8 | Campus Careers Week | 2.802% | 4.624% | On target | OK
2026-10-12 | C04 | LinkedIn | 11020 | 179 | 155 | 3 | Careers Site Refresh | 1.624% | 1.935% | Below target | OK
2026-10-19 | C01 | Email | 6242 | 276 | 233 | 13 | Graduate Hiring Drive | 4.422% | 5.579% | On target | OK
2026-10-19 | C02 | Careers Website | 3714 | 91 | 84 | 2 | Employee Stories Series | 2.45% | 2.381% | Below target | OK
2026-10-19 | C03 | LinkedIn | 2771 | 39 | 30 | 0 | Campus Careers Week | 1.407% | 0% | Below target | OK
2026-10-19 | C04 | Instagram | 3263 | 33 | 25 | 1 | Careers Site Refresh | 1.011% | 4% | Below target | OK
2026-10-26 | C01 | Careers Website | 4655 | 94 | 65 | 3 | Graduate Hiring Drive | 2.019% | 4.615% | On target | OK
2026-10-26 | C02 | LinkedIn | 7922 | 196 | 168 | 9 | Employee Stories Series | 2.474% | 5.357% | On target | OK
2026-10-26 | C03 | Instagram | 4799 | 72 | 66 | 3 | Campus Careers Week | 1.5% | 4.545% | Below target | OK
2026-10-26 | C04 | Email | 8356 | 436 | 409 | 6 | Careers Site Refresh | 5.218% | 1.467% | Below target | OK

## Careers_QA
Careers Website Quality Check
One row per check. Mark each Pass, Needs update or Fail, and add a note for anything not passing.
SAMPLE DATA: made-up entries for a fictional company, to show how the tracker works. Replace with your own.
Page | Check | Result | Date checked | Notes
Home page | Apply button works and opens the right page | Pass | 2026-10-20
Home page | Page loads correctly on a phone | Pass | 2026-10-20
Graduate page | Closing dates are correct and current | Needs update | 2026-10-20 | Update before next campaign push
Graduate page | Role descriptions match the latest job posts | Pass | 2026-10-20
Graduate page | Spelling and grammar checked | Pass | 2026-10-20
Life at the company | Employee story links open correctly | Pass | 2026-10-20
Life at the company | Photos have the right captions | Needs update | 2026-10-20 | Update before next campaign push
Life at the company | Employee consent noted for every story | Pass | 2026-10-20
FAQ | Answers match the current hiring process | Needs update | 2026-10-20 | Update before next campaign push
FAQ | Contact email is correct | Pass | 2026-10-20
Application form | Form submits and confirmation message appears | Pass | 2026-10-20
Application form | Required fields are clearly marked | Pass | 2026-10-20
Campus page | Event dates and venues are correct | Fail | 2026-10-20 | Wrong dates shown; raise with web team
Campus page | Registration link works | Pass | 2026-10-20
All pages | Footer links and privacy notice work | Pass | 2026-10-20

## Tasks
Tasks and Follow-ups
One row per task with a recruiter, agency, supplier or internal team. Overdue uses the report date on Settings.
SAMPLE DATA: made-up entries for a fictional company, to show how the tracker works. Replace with your own.
Task | Campaign ID | Partner type | Contact / team | Due date | Status | Overdue? | Days overdue
Confirm event dates for campus week | C03 | Recruiter | Campus hiring team | 2026-10-01 | Done
Get approved photos for employee stories | C02 | Internal | Communications | 2026-10-10 | Done
Receive final video edit for graduate drive | C01 | Supplier | Video editor | 2026-10-14 | Done
Share draft email copy for review | C01 | Internal | Brand team | 2026-10-18 | Done
Get consent form back from featured employee | C02 | Internal | HR partner | 2026-10-20 | Open | Overdue | 5
Send updated job descriptions for careers page | C04 | Recruiter | Talent acquisition | 2026-10-21 | Open | Overdue | 4
Approve social ad creatives | C01 | Agency | Social media agency | 2026-10-23 | Open | Overdue | 2
Fix wrong event dates on campus page | C03 | Internal | Web team | 2026-10-22 | Open | Overdue | 3
Send weekly results summary | C01 | Internal | Campaign manager | 2026-10-26 | Open
Book photographer for next story shoot | C02 | Supplier | Photography vendor | 2026-10-30 | Open
Review FAQ answers with recruiters | C04 | Recruiter | Talent acquisition | 2026-10-28 | Open
Share November content calendar | C02 | Internal | Brand team | 2026-11-02 | Open